## all
Milestone | Task | Start Date | End Date | Duration | Description | Member(s)
| Make Official User Stories | 2021-04-13 | 2021-04-13 | 1 |  | All
| Create Simple Sketches For User Stories | 2021-04-13 | 2021-04-14 | 2 |  | All
| Decide On Primary Design From Sketches | 2021-04-14 | 2021-04-15 | 2 |  | All
| Find List Of Stocks .csv | 2021-04-15 | 2021-04-15 | 1 |  | IZ
| Prelininary Reading Of Dataset | 2021-04-15 | 2021-04-17 | 3 |  | JM
| System To Pre-Calculate Index File Of All Stock Occurrences In All Messages | 2021-04-19 | 2021-04-20 | 2 |  | JM
| Research How To Go To Yahoo Finance With Selected Stock | 2021-04-20 | 2021-04-20 | 1 |  | CH
| Integrate Stock Urls Into The Webpage | 2021-04-20 | 2021-04-20 | 1 |  | JM
| Add More Comments/Improve Structure Of Code | 2021-04-20 | 2021-04-20 | 1 |  | JM
| Create List Of Common English Words | 2021-04-20 | 2021-04-27 | 8 |  | CH
| Create Test Cases For Code | 2021-04-20 | 2021-04-23 | 4 |  | JM
| Test Program | 2021-04-15 | 2021-04-27 | 13 |  | JM
| Final App Features And Tweaks | 2021-04-21 | 2021-04-29 | 9 |  | JM
| Outline Presentation | 2021-04-20 | 2021-04-28 | 9 |  | DT
| Final Report User Tests Area | 2021-04-27 | 2021-04-29 | 3 |  | JM
| Final Report Project Resources Area | 2021-04-27 | 2021-04-29 | 3 |  | JM, CH
| Project Implementation | 2021-04-15 | 2021-04-27 | 13 |  | JM
| Github Documenation | 2021-04-02 | 2021-05-02 | 31 |  | All
| Final Report System Design Area | 2021-04-27 | 2021-05-02 | 6 |  | IZ, DT, JM
| Final Report Introduction Area | 2021-04-27 | 2021-05-02 | 6 |  | CH
| Final Report Appendices | 2021-04-27 | 2021-05-02 | 6 |  | JM
| Complete Presentation Slides | 2021-04-29 | 2021-05-02 | 4 |  | All
| Final Report Plan Area | 2021-04-27 | 2021-05-02 | 6 |  | CH
| Final Report Lessons Learned And Future Work Areas | 2021-04-27 | 2021-05-02 | 6 |  | All
| Film Demo | 2021-05-02 | 2021-05-02 | 1 |  | DT
| Film Final Presentation | 2021-05-02 | 2021-05-02 | 1 |  | IZ
| Final Report | 2021-04-06 | 2021-05-02 | 25 |  | All
| Final Presentation | 2021-04-15 | 2021-05-02 | 18 |  | All
| Final Demo | 2021-04-29 | 2021-05-02 | 4 |  | DT
| Project Proposal | 2021-04-01 | 2021-04-01 | 1 |  | All
| Project Ideas | 2021-03-28 | 2021-03-30 | 3 |  | All
| Team Charter | 44281 | 2021-03-30 | 5 |  | All
| Project Pitchs | 2021-04-04 | 2021-04-06 | 3 |  | All
| Final Reads And Edits Of Project Report | 2021-05-01 | 2021-05-02 | 2 |  | All
| Final Reads And Edits Of Project Presentation | 2021-05-01 | 2021-05-02 | 2 |  | All

## milestones
Milestone | Start Date | End Date | Duration | Description | Members
Team Charter | 44281 | 2021-03-30 | 5 | The basis of how the team will interact with each other, how aspects of the project will be handled, what the expectations are for how the project will be handled, and any dedicated roles of group members. | All
Project Ideas | 2021-03-28 | 2021-03-30 | 3 | A set of four potential project ideas, one from each team member, based on a dataset that may offer a useful application. | All
Project Proposal | 2021-04-01 | 2021-04-01 | 1 | An explanation of why the chosen project idea is important, along with a product vision that describes the purpose of the project, who could benefit from the project, and the scope of the project. | All
Project Pitchs | 2021-04-04 | 2021-04-06 | 3 | A pitch from each team member about how they view the problem the project will solve and the potential benefits to any use | All
Design UX | 2021-04-13 | 2021-04-15 | 3 | Design the structure of the program web page. | All
Project Implementation | 2021-04-15 | 2021-04-27 | 13 | Source code of the project with any instructions needed for install and execution. | JM
Github Documenation | 2021-04-02 | 2021-05-02 | 31 | All documentation involved with creating the project. | All
Final Report | 2021-04-06 | 2021-05-02 | 27 | A full report of what the project is about, the objectives, resources, a timeline, milestone descriptions, diagrams, storyboard, testing, and etc. | All
Final Presentation | 2021-04-15 | 2021-05-02 | 18 | Final slide presentation that needs to be a summary of the final report. | All
Final Presentation and Demo | 2021-04-29 | 2021-05-02 | 4 | Recording of presentation and a working project. | All

## tasks
Milestone | Task | Start Date | End Date | Duration | Description | Member(s)
Milestone 4: Design UX | Make Official User Stories | 2021-04-13 | 2021-04-13 | 1 | Make Official User Stories: Create three or more user stories for how a user could use a product like how our idea would be used. | All
| Create Simple Sketches For User Stories | 2021-04-13 | 2021-04-14 | 2 | Create Simple Sketches for User Stories: Using the user stories, create a simple but as fully developed idea of what the webpage could look like | All
| Decide On Primary Design From Sketches | 2021-04-14 | 2021-04-15 | 2 | Decide on Primary Design from Sketches: Discuss and and decide on what elements from each member's sketch would be best suited to create a simple, streamlined webpage for the project idea. | All
Milestone 5: Project Implementation | Find List Of Stocks .csv | 2021-04-15 | 2021-04-15 | 1 | Read the Reddit posts from the dataset and begin to work with the data to count the number of occurrences for each stock symbol. | IZ
| Prelininary Reading Of Dataset | 2021-04-15 | 2021-04-17 | 3 | Find List of Stock .csv: Find a source that offers a dataset containing the currently held stocks, along with their corresponding company/industry/ticker information, in the NASDAQ and NYSE. | JM
| System To Pre-Calculate Index File Of All Stock Occurrences In All Messages | 2021-04-19 | 2021-04-20 | 2 | System to Pre-Calculate Index File of All Stock Occurrences in All Messages: Create an algorithm that will use the stock information to form an index that will hold the needed information about each stock and the number of occurrences in the Reddit posts. | JM
| Research How To Go To Yahoo Finance With Selected Stock | 2021-04-20 | 2021-04-20 | 1 | Research How to go to Yahoo Finance with Selected Stock: Research how to be able to take the user to a specific stock’s Yahoo Finance page instead of taking the user to the main Yahoo Finance page when they have selected a specific stock. | CH
| Integrate Stock Urls Into The Webpage | 2021-04-20 | 2021-04-20 | 1 | Integrate Stock URLs Into the Webpage: Based on the research of how to formulate the URL to a specific stock’s Yahoo Finance page, implement the functionality into the program. | JM
| Add More Comments/Improve Structure Of Code | 2021-04-20 | 2021-04-20 | 1 | Add More Comments/Improve Structure of Code: Ensure that there are the appropriate comments describing what the code is doing and the purpose behind it. Ensure that the structure of the code reduces any excess code and minimizes any bad “smells”. | JM
| Create List Of Common English Words | 2021-04-20 | 2021-04-27 | 8 | Create List of Common English Words: Research the most common written words in the English language and create a list to use to filter them from the Reddit dataset as it is read into the program. | CH
| Create Test Cases For Code | 2021-04-20 | 2021-04-23 | 4 | Making test cases for parts of the code to ensure functions and algorithms perform correctly across possible inputs, yielding the expected outputs | JM
| Test Program | 2021-04-15 | 2021-04-27 | 13 | With our partner team, Team CIS_Vikings, review the current iteration of the program and discuss any problems or features that need to be addressed. | JM
| Final App Features And Tweaks | 2021-04-21 | 2021-04-29 | 9 | Small remaining adjustments to the code to ensure that the webpage and program are intuitive to use. | JM
Milestone 7: Final Report | Final Report User Tests Area | 2021-04-27 | 2021-04-29 | 3 | An explanation of how the user can interact with the project, a summary of the user testing with our partner team, Team CIS_Vikings, and any final conclusions drawn from their feedback. | JM
| Final Report Project Resources Area | 2021-04-27 | 2021-04-29 | 3 | Identifies the team of this project, what the dataset is about, any software/hardware requirements to run the project locally, and any special resources that the project used in addition to the main dataset | JM, CH
| Final Report System Design Area | 2021-04-27 | 2021-05-02 | 6 | Describes the underlying structure of the program and how the program and datasets interact. It also includes the user stories that the project is based on, the feature list and a storyboard about how a user could interact with the webpage. | IZ, DT, JM
| Final Report Introduction Area | 2021-04-27 | 2021-05-02 | 6 | Using the proposal as a basis, review and make any necessary changes to any of the introduction subsections to present a better overall introduction to the project. | CH
| Final Report Appendices | 2021-04-27 | 2021-05-02 | 6 | This section contains the design sketches for the UX, the repository for the entire project, the instructions of how to install and run the program, the WBS tool used with a description of how it was used, and final screenshots of the webpage as it should look upon running the program. | JM
| Final Report Plan Area | 2021-04-27 | 2021-05-02 | 6 | A set of Gantt charts used to visualize how time was spent for each milestone/task, descriptions of each milestone and task, and who contributed predominantly in tasks. | CH
| Final Report Lessons Learned And Future Work Areas | 2021-04-27 | 2021-05-02 | 6 | An explanation of what issues the team encountered while working on the project and how they were resolved, along with how the team could envision further improvements that could be made to the program so that it would have more features and functionality. | All
| Final Reads And Edits Of Project Report | 2021-05-01 | 2021-05-02 | 2 | A series of final reads and edits of the final report to further refine the content. | All
Milestone 8: Final Presentation | Outline Presentation | 2021-04-20 | 2021-04-28 | 9 | A basic outline of the presentation based on suggestions from the instructor. | DT
| Complete Presentation Slides | 2021-04-29 | 2021-05-02 | 4 | Tailoring the presentation slides to present the most important information about the project and program. | All
| Final Reads And Edits Of Project Presentation | 2021-05-01 | 2021-05-02 | 2 | A series of final reads and edits of the presentation to further refine the content and present any ideas of how to effectively communicate the information to the viewer without overwhelming them with too much information. | All
Milestone 9: Final Presentation and Demo | Film Demo | 2021-05-02 | 2021-05-02 | 1 | Film/recording of the demonstration of the webpage and how the user can interact with it and an explanation of its features. | IZ
| Film Final Presentation | 2021-05-02 | 2021-05-02 | 1 | Film/recording of the presentation of the project, including the demonstration of the program, with an explanation of why the project is important, what its purpose is, how the program is designed, what enhancements could be made, and what was learned during the course of the project. | DT